## Timeline
TICKIFY — Event Marketing Timeline
8-week countdown to event day. Tick the Done column as you go. Add your event date to column B row 4.
Phase | Days Out | Task | Channel / Tool | Owner | Done
8 Weeks Out
8 Weeks Out | 56 | Confirm venue, date, and final lineup | Internal
8 Weeks Out | 56 | Set ticket tiers and pricing in Tickify | Tickify
8 Weeks Out | 56 | Create event page with full details and cover image | Tickify / Eventbrite
8 Weeks Out | 56 | Draft press release | Doc
8 Weeks Out | 56 | Brief sponsors on event details | Email
6 Weeks Out
6 Weeks Out | 42 | Go on sale — Early Bird tickets live | Tickify
6 Weeks Out | 42 | Announce on all social channels | Instagram / TikTok
6 Weeks Out | 42 | Send to email list | Email
6 Weeks Out | 42 | Send press release to media contacts | Email / PR
6 Weeks Out | 42 | Launch paid social campaign (awareness phase) | Meta Ads
6 Weeks Out | 42 | Post to relevant Facebook groups and communities | Facebook
4 Weeks Out
4 Weeks Out | 28 | Early Bird close — switch to General Admission | Tickify
4 Weeks Out | 28 | Mid-campaign content push (artist features, etc.) | Instagram / TikTok
4 Weeks Out | 28 | Retarget website visitors with paid ads | Meta Ads
4 Weeks Out | 28 | Partner / support act social cross-promotion | Instagram
4 Weeks Out | 28 | Send 2nd email to list (urgency / social proof) | Email
4 Weeks Out | 28 | Confirm sponsor deliverables and placement | Email
2 Weeks Out
2 Weeks Out | 14 | Open VIP / Premium tier (if holding back) | Tickify
2 Weeks Out | 14 | Increase paid ad spend — conversion phase | Meta Ads
2 Weeks Out | 14 | Countdown content (14-day, 7-day posts) | Instagram / TikTok
2 Weeks Out | 14 | Send 3rd email — 2 weeks to go | Email
2 Weeks Out | 14 | Coordinate media / photographer brief | Email
2 Weeks Out | 14 | Confirm all logistics: security, AV, venue | Internal
1 Week Out
1 Week Out | 7 | Final push content — 7, 5, 3, 1 day countdown | Instagram / TikTok
1 Week Out | 7 | Send 4th email — last chance | Email
1 Week Out | 7 | Stories / reels — social proof, lineup reminders | Instagram Stories
1 Week Out | 7 | Confirm door list and ticket scan setup | Tickify / Internal
1 Week Out | 7 | Brief all staff and volunteers | Internal
Event Week
Event Week | 3 | Final email: what to expect, doors, transport | Email
Event Week | 3 | Boost posts with urgency spend | Meta Ads
Event Week | 1 | Day-before reminder story / post | Instagram Stories
Event Week | 0 | Check ticket scan app is set up and working | Tickify
Event Week | 0 | Brief door team on ticket types and VIP flow | Internal
Day Of
Day Of | 0 | Go live on Instagram / TikTok at venue | Instagram Live
Day Of | 0 | Capture content: crowd, artists, sponsor placements | Photo / Video
Day Of | 0 | Monitor door and ticket scan in Tickify dashboard | Tickify
Day Of | 0 | Thank sponsors with on-the-day shoutouts | Instagram Stories
Post-Event
Post-Event | +1 days after | Export attendee data from Tickify | Tickify
Post-Event | +1 days after | Send thank-you email to all attendees | Email
Post-Event | +1 days after | Post highlight reel / recap content | Instagram / TikTok
Post-Event | +7 days after | Send post-event sponsor report | Email
Post-Event | +7 days after | Review ticket sales data — what sold first? | Tickify dashboard
Post-Event | +7 days after | Add attendees to CRM / email list for next event | Email platform
Post-Event | +14 days after | Debrief team — what worked, what didn't | Internal
Post-Event | +14 days after | Start planning next event with this data | Budget Planner

## Instructions
How to use this timeline
This is an 8-week countdown template. Start it the moment you confirm your venue and date.
HOW TO USE IT
1. Make a copy (File > Make a copy in Google Sheets).
2. Fill in the Owner column with whoever is responsible for each task.
3. Work backwards from your event date — the Days Out column tells you when each task is due.
4. Tick the Done column as you complete tasks. Use a checkmark (✓) or any symbol.
WHAT TO CUSTOMISE
• Add or remove tasks to match your event type (festival vs club night vs conference).
• Update the Channel column to match the tools you actually use.
• Add a Date column if you want exact calendar dates.
KEY PRINCIPLES
• Go on sale early. 8 weeks minimum for any event over 200 people.
• Early Bird is your most important sale. It creates social proof and momentum.
• Email outperforms social for converting existing fans. Use both.
• Post-event is where most promoters drop the ball. The sponsor report and thank-you email take 2 hours and pay dividends.
Built by Tickify — the event ticketing platform built for promoters. tickify.io